## Sheet1
Actionable Project Plan
Week | Tasks | TESTING
05.01.-11.01. | Fix database, implement web and ai request rate limiting | FUNCTIONAL
12.01.-18.01. | Intermediate Presentation | DEADLINE
19.01.-25.01. | Fully automated testing via CI/CD + 20 apps with default creds
26.01.-01.02. | Try and evaluate other methods/prompts using the testing setup
02.02.-08.02. | Implement persistence/long time scanning
09.02.-15.02. | Evaluation + Buffer
16.02.-22.02. | Final Presentation